## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Introduction to project & problem statement discussion | MUST HAVE | No Dependancy | Blessy Christrus | 3 - Completed
S1 | S1 | US-002 | Introduction to project & problem statement discussion | MUST HAVE | Lucidchart | Shital | 3 - Completed
S1 | S1 | US-003 | Tech stack finalization (Spring Boot, MySQL, ML) | MUST HAVE | No Dependancy | Nithya Sri | 3 - Completed
S1 | S1 | US-004 | Create Spring Boot project & configure MySQL | MUST HAVE | MySQL | Blessy Christrus | 3 - Completed
S1 | S1 | US-005 | Create transaction & alert tables using JPA | MUST HAVE | Spring Data JPA | Shital | 3 - Completed
S2 | S2 | US-006 | Verify application runs without errors | MUST HAVE | Backend Setup | Nithya Sri | 3 - Completed
S2 | S2 | US-007 | Develop Transaction REST API (/api/transactions) | MUST HAVE | Spring REST | Blessy Christrus | 3 - Completed
S2 | S2 | US-008 | Implement transaction generator (normal & fraud) | SHOULD HAVE | API Endpoint | Shital | 3 - Completed
S2 | S2 | US-009 | Store generated transactions in database | MUST HAVE | MySQL | Nithya Sri | 3 - Completed
S2 | S2 | US-010 | Implement fraud detection rules engine | MUST HAVE | Detection Service | Blessy Christrus | 3 - Completed
S3 | S3 | US-011 | Generate alerts with risk score & explanation | MUST HAVE | Rule Engine | Shital | 3 - Completed
S3 | S3 | US-012 | Store fraud alerts in database | MUST HAVE | MySQL | Nithya Sri | 3 - Completed
S3 | S3 | US-013 | Create alert APIs with filters | MUST HAVE | REST APIs | Blessy Christrus | 3 - Completed
S3 | S3 | US-014 | Develop fraud dashboard UI | SHOULD HAVE | Frontend | Shital | 3 - Completed
S3 | S3 | US-015 | Risk color coding & alert visualization | SHOULD HAVE | Dashboard | Nithya Sri | 3 - Completed
S3 | S3 | US-016 | Fraud scenario testing & validation | MUST HAVE | Rule Engine | Blessy Christrus | 3 - Completed
S4 | S4 | US-017 | Generate evaluation metrics & analytics | SHOULD HAVE | Alerts Data | Shital | 3 - Completed
S4 | S4 | US-018 | Implement basic ML model for fraud prediction | COULD HAVE | ML | Nithya Sri | 3 - Completed
S4 | S4 | US-019 | Prepare final demo & architecture explanation | MUST HAVE | All Modules | Blessy Christrus | 3 - Completed
S4 | S4 | US-020 | Project documentation & submission | MUST HAVE | Completed System | Shital | 3 - Completed
S4 | S4 | US-021 | Final review & presentation | MUST HAVE | Team Review | Nithya Sri | 3 - Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 64 | 2.5 | 3 | 3 | 2 | 9 | 7 | 7 | 8 | 7 | 2 | 3 | 1.5 | 2 | 1.5
SPRINT 1 BACKLOG
US-001 | US-001-T1 | Understand problem statement | 2025-11-27 | 2025-11-27 | Blessy | Discussion | Completed | 1 | bar: Day 1
US-001 | US-001-T2 | Finalize project scope | 2025-11-27 | 2025-11-27 | Blessy | Planning | Completed | 1.5 | Day 1: 1.5
US-002 | US-002-T1 | Prepare problem statement document | 2025-11-28 | 2025-11-28 | Shital | Documentation | Completed | 2 | Day 2: 2
US-002 | US-002-T2 | Review and finalize document | 2025-11-28 | 2025-11-28 | Shital | Review | Completed | 1 | bar: Day 2
US-003 | US-003-T1 | Analyze tech stack options | 2025-11-29 | 2025-11-29 | Nithya | Analysis | Completed | 2 | Day 3: 2
US-003 | US-003-T2 | Finalize Spring Boot, MySQL, ML | 2025-11-29 | 2025-11-29 | Nithya | Decision | Completed | 1 | bar: Day 3
US-004 | US-004-T1 | Create Spring Boot project | 2025-12-02 | 2025-12-02 | Blessy | Development | Completed | 2 | Day 4: 2
US-004 | US-004-T2 | Add JPA & MySQL dependencies | 2025-12-02 | 2025-12-02 | Blessy | Configuration | Completed | 1 | bar: Day 5
US-004 | US-004-T3 | Configure database connection | 2025-12-03 | 2025-12-03 | Blessy | Configuration | Completed | 2 | Day 5: 2
US-004 | US-004-T4 | Test database connectivity | 2025-12-03 | 2025-12-03 | Blessy | Testing | Completed | 1 | bar: Day 5
US-005 | US-005-T1 | Design transaction entity | 2025-12-04 | 2025-12-04 | Shital | Design | Completed | 2 | Day 5: 2
US-005 | US-005-T2 | Create JPA repository | 2025-12-04 | 2025-12-04 | Shital | Development | Completed | 1 | bar: Day 6
US-005 | US-005-T3 | Verify table creation | 2025-12-04 | 2025-12-04 | Shital | Testing | Completed | 1 | bar: Day 6
US-006 | US-006-T1 | Run backend services | 2025-12-05 | 2025-12-05 | Nithya | Testing | Completed | 2 | Day 6: 2; Day 7: 2
US-006 | US-006-T2 | Fix backend errors | 2025-12-05 | 2025-12-05 | Nithya | Debugging | Completed | 2 | Day 7: 2
US-007 | US-007-T1 | Create REST controller | 2025-12-06 | 2025-12-06 | Blessy | Development | Completed | 2 | Day 8: 2
US-007 | US-007-T2 | Implement API endpoints | 2025-12-06 | 2025-12-06 | Blessy | Development | Completed | 2 | bar: Day 8
US-007 | US-007-T3 | Test API using Postman | 2025-12-06 | 2025-12-06 | Blessy | Testing | Completed | 1 | Day 8: 2
US-008 | US-008-T1 | Generate normal transactions | 2025-12-09 | 2025-12-09 | Shital | Development | Completed | 2 | Day 9: 2
US-008 | US-008-T2 | Generate fraud transaction | 2025-12-09 | 2025-12-09 | Shital | Development | Completed | 2 | Day 9: 2
US-009 | US-009-T1 | Store transactions in DB | 2025-12-10 | 2025-12-10 | Nithya | Development | Completed | 2
US-009 | US-009-T2 | Validate stored records | 2025-12-10 | 2025-12-10 | Nithya | Testing | Completed | 1
US-010 | US-010-T1 | Implement rule-based fraud checks | 2025-12-10 | 2025-12-10 | Blessy | Development | Completed | 2
US-010 | US-010-T2 | Validate rules with sample data | 2025-12-10 | 2025-12-10 | Blessy | Testing | Completed | 1
US-011 | US-011-T1 | Create risk scoring logic | 2025-12-10 | 2025-12-10 | Shital | Development | Completed | 2
US-011 | US-011-T2 | Add alert explanation messages | 2025-12-10 | 2025-12-10 | Blessy | Development | Completed | 1 | Day 5: 2
US-012 | US-012-T1 | Design alert entity | 2025-12-09 | 2025-12-09 | Nithya | Design | Completed | 1.5 | bar: Day 5
US-012 | US-012-T2 | Save alerts in MySQL | 2025-12-09 | 2025-12-09 | Nithya | Development | Completed | 1.5 | Day 6: 1.5
US-013 | US-013-T1 | Develop alert REST APIs | 2025-12-09 | 2025-12-09 | Blessy | Development | Completed | 2 | Day 6: 1.5
US-013 | US-013-T2 | Implement filter options | 2025-12-09 | 2025-12-09 | Blessy | Development | Completed | 1 | Day 7: 2
US-014 | US-014-T1 | Design dashboard UI layout | 2025-12-10 | 2025-12-10 | Shital | UI Design | Completed | 2 | bar: Day 7
US-014 | US-014-T2 | Integrate backend APIs | 2025-12-10 | 2025-12-10 | Shital | Integration | Completed | 1 | Day 8: 2
US-015 | US-015-T1 | Implement risk color coding | 2025-12-11 | 2025-12-11 | Nithya | UI Enhancement | Completed | 1.5 | bar: Day 8
US-015 | US-015-T2 | Validate visualization output | 2025-12-11 | 2025-12-11 | Nithya | Testing | Completed | 1 | bar: Day 9
US-016 | US-016-T1 | Create fraud test scenarios | 2025-12-12 | 2025-12-12 | Blessy | Testing | Completed | 2 | Day 9: 2
US-017 | US-017-T1 | Calculate fraud detection metrics | 2025-12-13 | 2025-12-13 | Shital | Analysis | Completed | 2 | Day 10: 2
US-018 | US-018-T1 | Train ML model | 2025-12-16 | 2025-12-16 | Nithya | ML Development | Completed | 3 | Day 11: 3
US-019 | US-019-T1 | Prepare demo flow | 2025-12-16 | 2025-12-16 | Blessy | Preparation | Completed | 1.5 | Day 12: 1.5
US-020 | US-020-T1 | Prepare project documentation | 2025-12-16 | 2025-12-16 | Shital | Documentation | Completed | 2 | Day 13: 2
US-021 | US-021-T1 | Final review and presentation | 2025-12-16 | 2025-12-16 | Nithya | Presentation | Completed | 1.5 | Day 14: 1.5
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
S1 | Day 2 | Delay in finalizing tech stack | Conducted quick team discussion and finalized Spring Boot + MySQL
S2 | Day 4 | REST API error (JSON parsing) | Debugged controller, fixed serialization issue
S3 | Day 7 | Dashboard UI not rendering alerts | Adjusted API response format, fixed frontend binding
S4 | Day 10 | ML model accuracy low | Tuned parameters, improved dataset quality

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | S1 | 2025-11-27 | 2025-12-10 | Shital | Clear requirement discussion before coding | Vague task understanding | Team discussions | Finalized problem statement and scope
2 | S2 | 2025-12-11 | 2025-12-31 | Blessy | Early API testing | Delaying backend validation | Code reviews | Implemented REST APIs with testing
3 | S3 | 2026-01-01 | 2026-01-15 | Shital | UI testing with real data | Hard-coded UI values | Incremental UI improvements | Dashboard and alert visualization completed
4 | S4 | 2026-01-16 | 2026-01-27 | Nithya | Maintain ML experiment logs | Training model with unclean data | Parameter tuning | Improved ML accuracy and finalized documentation